## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US01 | As a developer, I want to set up the project environment with FastAPI, LangChain and Groq so that I have a foundation to build the AI agent. | Must | Environment Setup | Me | Completed
Sprint 1 | Sprint 1 | US02 | As a user, I want to submit a prompt to the agent through an API so that I can get an LLM-generated response. | Must | FastAPI, Groq LLM | Me | Completed
Sprint 1 | Sprint 1 | US03 | As a developer, I want a basic Agent class that wraps the LLM so that agent behavior can be reused and extended later. | Must | LangChain | Me | Completed
Sprint 1 | Sprint 1 | US04 | As a developer, I want input validation on the API so that malformed requests are rejected before reaching the LLM. | Must | Pydantic | Me | Completed
Sprint 1 | Sprint 1 | US05 | As a developer, I want to test the agent via Swagger UI so that I can verify normal and edge-case behavior. | Should | FastAPI Docs | Me | Completed
Sprint 2 | Sprint 2 | US06 | As a user, I want the agent to fetch real-time weather data so that it can answer location-based questions accurately. | Must | Open-Meteo API | Me | Completed
Sprint 2 | Sprint 2 | US07 | As a user, I want the agent to perform calculations so that it can answer arithmetic questions. | Should | Calculator Tool | Me | Completed
Sprint 2 | Sprint 2 | US08 | As a developer, I want the agent to decide on its own whether a tool is needed so that tool use isn't hardcoded. | Must | LangGraph ReAct Agent | Me | Completed
Sprint 2 | Sprint 2 | US09 | As a developer, I want validation and error handling around tool calls so that invalid input or API failures don't crash the app. | Must | Tool Integration | Me | Completed
Sprint 2 | Sprint 2 | US10 | As a user, I want the agent to ask for clarification when my question is ambiguous (e.g. no city given) so that it doesn't guess incorrectly. | Should | Agent Prompt Design | Me | Completed
Sprint 3 | Sprint 3 | US11 | As a user, I want to submit a leave request in plain language so that the system can process it automatically. | Must | Planning Agent | Me | Completed
Sprint 3 | Sprint 3 | US12 | As a user, I want specialized agents (Research, Analysis, Decision) to evaluate my leave request so that I receive an accurate, policy-based decision. | Must | Multi-Agent Workflow | Me | Completed
Sprint 3 | Sprint 3 | US13 | As a user, I want a Coordinator Agent to dynamically decide which agents to run so that simple requests don't trigger unnecessary steps. | Must | LangGraph StateGraph | Me | Completed
Sprint 3 | Sprint 3 | US14 | As a user, I want the system to remember my conversation within a session so that follow-up requests don't need repeated details. | Must | Short-Term Memory (PostgresSaver) | Me | Completed
Sprint 3 | Sprint 3 | US15 | As a user, I want my past leave decisions to be remembered across separate conversations so that the system has full context about my history. | Should | Long-Term Memory (Postgres) | Me | Completed
Sprint 3 | Sprint 3 | US16 | As a user, I want to log in securely so that only I can access and act on my own leave data. | Must | bcrypt, JWT | Me | Completed
Sprint 3 | Sprint 3 | US17 | As a user, I want a web interface with a calendar so that I can submit, extend, and cancel leave requests visually. | Must | HTML/CSS/JS Frontend | Me | Completed
Sprint 4 | Sprint 4 | US18 | As a user, I want to log in using my email so that I don't need to remember an internal employee ID. | Should | Authentication | Me | Completed
Sprint 4 | Sprint 4 | US19 | As an administrator, I want every agent and tool action logged so that I can audit what happened during a request. | Must | Audit Logging | Me | Completed
Sprint 4 | Sprint 4 | US20 | As an administrator, I want a monitoring dashboard showing system-wide statistics so that I can track performance and reliability. | Should | Monitoring Stats | Me | Completed
Sprint 4 | Sprint 4 | US21 | As a system, I want rate limiting on sensitive endpoints so that the API is protected from abuse. | Must | slowapi | Me | Completed
Sprint 4 | Sprint 4 | US22 | As a user, I want the application to handle failures gracefully everywhere so that I never see a raw crash. | Must | Error Handling | Me | Completed
Sprint 4 | Sprint 4 | US23 | As a user, I want a polished, professional interface so that the application feels production-ready. | Should | Frontend Redesign | Me | Completed
Sprint 4 | Sprint 4 | US24 | As a user, I want the application deployed to the cloud so that I can access it remotely. | Must | Render/Railway Deployment | Me | Completed

## Sprint Backlog
US ID | Task ID | Task Description | Team Member | Activity | Status | Estimate (Hours)
US01 | T01 | Set up FastAPI project structure and folders (agents/prompts/tools/memory/api/config) | Me | Backend | Completed | 3
US01 | T02 | Configure Groq API key loading via python-dotenv | Me | Backend | Completed | 2
US02 | T03 | Implement POST /ask endpoint with Pydantic request/response models | Me | Backend | Completed | 4
US03 | T04 | Build Agent class wrapping the ChatGroq LLM | Me | AI/Agent | Completed | 4
US04 | T05 | Add Pydantic validation for request fields | Me | Backend | Completed | 3
US05 | T06 | Test agent via Swagger UI with 6 test cases (normal, vague, empty, long, missing field, wrong type) | Me | Testing | Completed | 3
US06 | T07 | Build standalone weather tool using Open-Meteo geocoding + current weather API | Me | API Integration | Completed | 5
US06 | T08 | Wrap weather tool with LangChain @tool decorator | Me | AI/Agent | Completed | 2
US07 | T09 | Build calculator tool with safe expression validation | Me | Backend | Completed | 3
US08 | T10 | Integrate LangGraph create_react_agent for tool-calling decisions | Me | AI/Agent | Completed | 5
US09 | T11 | Add error handling for invalid cities, timeouts, and network errors | Me | Backend | Completed | 3
US09 | T12 | Add custom RequestValidationError handler for friendly error messages | Me | Backend | Completed | 2
US10 | T13 | Add system instruction so agent asks for a city instead of guessing | Me | AI/Agent | Completed | 2
US11 | T14 | Build Planning Agent to extract leave dates and reason from free text | Me | AI/Agent | Completed | 5
US12 | T15 | Build Research Agent with 6 tools for leave data | Me | AI/Agent | Completed | 6
US12 | T16 | Build Analysis Agent applying deterministic policy rules | Me | AI/Agent | Completed | 5
US12 | T17 | Build Decision Agent to produce Approve/Reject/Escalate outcome | Me | AI/Agent | Completed | 5
US13 | T18 | Implement Coordinator Agent with hub-and-spoke LangGraph routing | Me | AI/Agent | Completed | 7
US13 | T19 | Add deterministic retry-limit and loop-protection logic | Me | Backend | Completed | 3
US14 | T20 | Configure PostgresSaver checkpointer for short-term memory | Me | Backend | Completed | 4
US15 | T21 | Build long_term_memory table and fetch_past_decisions tool | Me | Database | Completed | 4
US16 | T22 | Implement bcrypt password hashing and JWT issuing/verification | Me | Backend | Completed | 5
US16 | T23 | Add ownership checks (403) on extend/cancel/resolve-mixed endpoints | Me | Backend | Completed | 3
US17 | T24 | Build login, dashboard, and calendar-based new-request pages | Me | Frontend | Completed | 8
US17 | T25 | Implement double-booking prevention on the calendar | Me | Frontend | Completed | 4
US18 | T26 | Add email column and switch login to email-based authentication | Me | Backend | Completed | 3
US19 | T27 | Build shared log_event() function and wire into all 5 agents | Me | Backend | Completed | 6
US19 | T28 | Add per-session audit log viewer on the dashboard | Me | Frontend | Completed | 3
US20 | T29 | Build get_monitoring_stats() aggregation and /monitoring-stats endpoint | Me | Backend | Completed | 5
US20 | T30 | Build monitoring dashboard page with stat cards and tables | Me | Frontend | Completed | 4
US21 | T31 | Add slowapi tiered rate limiting across all endpoints | Me | Backend | Completed | 5
US22 | T32 | Add global exception handler and restore validation error handler | Me | Backend | Completed | 3
US22 | T33 | Fix idle database connection issue using a self-healing ConnectionPool | Me | Backend | Completed | 3
US23 | T34 | Redesign frontend with a professional visual style | Me | Frontend | Completed | 6
US24 | T35 | Configure production environment and deploy the application | Me | Deployment | In Progress | 5

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Deciding how to organize the project structure (agents/tools/config). | Organized the codebase into agents/prompts/tools/memory/api/config folders.
Sprint 1 | Day 2 | Python 3.14 is very new; uncertain about package compatibility. | Verified compatibility of core packages (FastAPI, LangChain, Groq) before proceeding.
Sprint 1 | Day 3 | Notepad introduced encoding glitches (en-dash, arrows) in markdown files. | Switched to plain ASCII characters in README and documentation.
Sprint 1 | Day 4 | Needed to confirm .env was never committed to Git. | Added .gitignore and checked git status before every push.
Sprint 1 | Day 5 | Testing edge cases (empty string, missing field, wrong data type). | Verified Pydantic returns clean 422 errors before the request ever reaches the LLM.
Sprint 2 | Day 1 | Deciding which tool to build first to genuinely satisfy the external API requirement. | Chose the weather tool via Open-Meteo since it requires a real external API call.
Sprint 2 | Day 2 | Ambiguous city names occasionally resolved to the wrong location (e.g. Bangalore, Pakistan). | Observed the agent self-correcting using conversational context; documented as a known limitation.
Sprint 2 | Day 3 | Agent guessed a default city instead of asking when none was mentioned. | Added a system instruction directing the agent to ask for clarification instead of guessing.
Sprint 2 | Day 4 | An empty tool result ([]) caused a Groq API 400 error. | Fixed all tools to return json.dumps() output so empty lists serialize safely.
Sprint 2 | Day 5 | Needed real proof that tool-calling was genuinely happening, not assumed. | Added temporary debug prints of the LangGraph message chain, verified behavior, then removed them.
Sprint 3 | Day 1 | Deciding the exact split of responsibility between the Coordinator and Planning Agent. | Kept 'how the system operates' (Coordinator) separate from 'content groundwork' (Planning), per mentor's instruction.
Sprint 3 | Day 2 | MemorySaver checkpointer wasn't persisting state across separate requests. | Upgraded to PostgresSaver backed by Neon Postgres for genuine cross-request persistence.
Sprint 3 | Day 3 | Coordinator's LLM retried past the intended retry limit. | Moved the retry-limit check into deterministic Python code instead of relying on LLM judgment.
Sprint 3 | Day 4 | Stale dates were being overwritten with None on follow-up messages. | Fixed the Planning Agent to preserve prior context unless new extraction actually found a value.
Sprint 3 | Day 5 | All 8 seeded employees ended up with identical password hashes. | Fixed bcrypt.hashpw() to run independently for each employee.
Sprint 3 | Day 6 | An authenticated employee could act on another employee's session by guessing its thread_id. | Added explicit 403 ownership checks on the extend, cancel, and resolve-mixed endpoints.
Sprint 3 | Day 7 | dashboard.js broke twice from manual paste errors. | Diagnosed via browser DevTools Console and replaced with a fully verified file each time.
Sprint 3 | Day 8 | Outcome detection failed when the LLM wrapped its answer in markdown bold (e.g. **APPROVE**). | Built a shared, markdown-tolerant detect_decision_outcome() function used everywhere the outcome is checked.
Sprint 4 | Day 1 | Extending a leave onto a weekend or holiday was incorrectly approved. | Added weekend and holiday checks to validate_single_day_extension().
Sprint 4 | Day 2 | Average workflow duration was inflated by later extend/cancel activity on the same thread. | Bounded the duration calculation to Coordinator agent rows only.
Sprint 4 | Day 3 | Several endpoints already used 'request' as a Pydantic body parameter name, conflicting with slowapi's requirements. | Renamed those parameters to 'payload' across the file, updating all internal references.
Sprint 4 | Day 4 | The RequestValidationError handler was lost during a full-file rewrite of api/main.py. | Re-added a handler that builds its message dynamically from the real validation error.
Sprint 4 | Day 5 | Idle Neon database connections were closing during low-traffic periods. | Replaced the single long-lived connection with a self-healing ConnectionPool.
Sprint 4 | Day 6 | Frontend looked generic and needed a professional redesign without breaking existing JavaScript. | Mapped every JS dependency first, then redesigned CSS/HTML only, with zero JS logic changes.

## Retrospection
SL | Sprint | Team Member | Start Doing | Stop Doing | Continue Doing | Action Taken
1 | Sprint 1 | Me | Test edge cases (empty input, missing fields, wrong types) earlier in the process. | Using Notepad for files containing special characters like en-dashes and arrows. | Testing each piece standalone via Swagger UI before trusting it works. | Adopted plain ASCII in documentation and verified all 6 edge cases via Swagger before moving on.
2 | Sprint 2 | Me | Verify tool outputs are JSON-safe before wiring them into the agent. | Assuming a third-party API will always return a clean, expected result. | Adding temporary debug prints to verify real behavior before trusting it. | Standardized all tools to return json.dumps() output and added a system instruction to stop the agent from guessing.
3 | Sprint 3 | Me | Write a standalone test script for every new function before integrating it. | Relying on LLM judgment for safety-critical logic such as retry limits. | Documenting real bugs honestly instead of only showing polished results. | Moved retry-limit enforcement into deterministic code and added ownership checks beyond what was originally flagged.
4 | Sprint 4 | Me | Run a syntax check before handing back or committing any edited file. | Trusting a 'summary of already-done work' without verifying it against the real code. | Closing out every failure-test case with real, reproduced evidence rather than assumptions. | Independently re-verified all claimed fixes against the actual codebase before documenting them in the README.