## Defects
Defect ID | Module | Defect Description | Severity | Status | Resolution
DEF-001 | Weather Tool | Empty tool result ([]) caused a Groq API 400 error when returned to the agent. | High | Closed | All tools updated to return json.dumps() output so empty lists serialize as a valid string.
DEF-002 | Agent Workflow | Agent guessed a default city instead of asking when none was mentioned in the request. | Medium | Closed | Added a system instruction directing the agent to ask for clarification instead of guessing.
DEF-003 | Coordinator Agent | Coordinator's LLM retried past the intended retry limit because it was never given the actual number. | High | Closed | Moved the retry-limit check into deterministic Python code, independent of LLM judgment.
DEF-004 | Memory | MemorySaver checkpointer silently lost state between separate process/request invocations. | High | Closed | Upgraded to PostgresSaver backed by Neon Postgres for genuine cross-request persistence.
DEF-005 | Planning Agent | Follow-up messages without new dates overwrote previously known start/end dates with None. | Medium | Closed | Fixed to preserve prior context unless new extraction actually found a value.
DEF-006 | Authentication | All 8 seeded employees were given identical bcrypt password hashes. | Low | Closed | Fixed bcrypt.hashpw() to hash each employee's password independently.
DEF-007 | Authorization | An authenticated employee could act on another employee's session by guessing its thread_id. | High | Closed | Added explicit 403 ownership checks on the extend, cancel, and resolve-mixed endpoints.
DEF-008 | Decision Agent | Outcome detection failed when the LLM wrapped its answer in markdown bold (e.g. **APPROVE**), silently defaulting to UNKNOWN. | High | Closed | Built a shared, markdown-tolerant detect_decision_outcome() function used everywhere the outcome is checked.
DEF-009 | Extend Feature | A one-day leave extension could be approved onto a weekend or an official holiday. | Medium | Closed | Added weekend and holiday checks to validate_single_day_extension().
DEF-010 | Monitoring | Average workflow duration was inflated by including later extend/cancel activity on the same thread. | Medium | Closed | Bounded the duration calculation to Coordinator agent rows only.
DEF-011 | API Error Handling | The RequestValidationError handler was lost entirely during a full-file rewrite of api/main.py. | Medium | Closed | Re-added a handler that builds its message dynamically from the real validation error.
DEF-012 | Database | PostgresSaver held one long-lived connection that Neon closed after idle periods, raising 'connection is closed' errors. | Medium | Closed | Replaced the single persistent connection with a self-healing psycopg_pool ConnectionPool.
DEF-013 | Rate Limiting | A duplicate rate_limit_exceeded_handler definition was left over from an earlier edit. | Low | Closed | Removed the duplicate block, keeping one clean handler definition.